## Walkthrough - 1
As at 20/02/2015
| Task/Error | Location | Comments
1 | Ensure all static boxes are appropriately linked to the back-end, as per wireframes | Homepage, pg. #6, 7, admin panel | The static boxes on the site currently are all the same - if change the content 'performance' on the backend, all static boxes on the site change to that. This should not be the case. Each page has different content to show for each static box.
2 | The system should generate a notification when supplier registration has expired | Admin panel | The notification is currently on all screens on the Admin Panel. Can we restrict this to only the Dashboard and the Reviews Screens? | done
3 | If there is an error on the form whilst submitting, all data is lost | Registration | The form does not capture data when there is an error in one field in the form. All correct data input by the customer is lost, such as 'I Live'
4 | If there is an error on the form whilst submitting, all data is lost | Write a Review | The form does not capture data when there is an error in one field in the form. There seems to be an error with the company/location/town after an error, as you need to refresh the browser several times before the dropdown options display again.
5 | Date of Incident | Write a Review | The correct way: A time in the future should not be selected. However, the system does not allow a customer to leave a review on the same day/date. This should be allowed - but the time should be past. For e.g. customer can report an incident that occurred on 20/02/15 at 11:30 at 20/02/15 at 14:00
6 | What is the difference between Reviews, unpublished reviews etc. | Admin panel | Can we change the titles so these are more clear? The Dashboard section titles are unclear on what type of reviews they display. | done
7 | Cannot edit the content of this page from the Admin Panel | CSR Page/Admin panel | I see a CSR section on the 'pages' admin panel, but the content does not reflect on the front end for the CSR page. | done
8 | Once complete a review and submit - then register for an account. The customer is left on the Account page - redirect to homepage | Write a Review | Once they register for an account and wait for account validation, customers are left with the Account screen, they should be redirected to the homepage whilst they validate their account. | discussion
9 | Clicking on the Company logo goes to Review page; it should redirect to the Homepage. | Logo |  | done
10 | When click on the Company Name on the review section on the homepage, the correct page opens; but the tab on the top-menu bar does not change to the Reviews page. It stays on the My Account Tab. | Homepage | The page opened should be correctly reflected on the Top-Menu bar. E.g. clicking on the hyperlink for company or review title opens the reviews page for that selection. Hence the top-menu bar should reflect that too. | done
11 | The date format on the filter is in American Format. Colander should be changed to British format; to be similar with the 'date of incident' on the write a review page. | Reviews/Filter |  | done
12 | If customer is already logged in to the system, should the form automatically capture their name and email address? | Contact US |  | done
13 | Polls - once customer selects their response, there is no reaction from the system. The customer should see the results so far on the polls. | Polls | The results for the polls are only visible on the Reviews page under polls and bloopers - once a customer answers a poll, they should be able to see the results so far of the poll. | discussion
14 | Supplier registration - date format. There is an option to select 31 days in February, and the system does not validate this as an error. | Admin Panel | The date is a dropdown, hence dates cannot be verified. Wrong dates can be selected for the supplier registration. Can we correct this? | add validation
15 | Supplier Registration - it so not mandatory to fill in 3 contact details for each supplier. Only one is mandatory. | Admin Panel | Currently 3 contact details need to be filled in to complete registration. Only one is essential/mandatory. Other 2 are optional.
16 | Is the SEO across the site? On all Pages? | Admin Panel
17 | The Admin has rights to see customer details - but there is no section on the side-menu bar for customers | Admin Panel | Only most recent customers can be seen on the dashboard. Needs to be a customer section where the Admin can see all customer details. | add a link
18 | Once a review is assigned - there is no section to see on the table who the review has been assigned to. | Admin Panel | If Admin/SR Agent assigns review, on the review summary table, cannot see who the review has been assigned to.
19 | If review has been assigned, the Agent once logged in cannot see which review they are meant to action. | Admin Panel | JR/SR Agents assigned review cannot be seen, difficult to know which review has been assigned to you to action.
20 | Trial Supplier Subscription - cannot respond on the supplier behalf. This should change. | Admin Panel | Supplier registered and on trial can respond to a review. | supplier new action
21 | Comments are to be vetted - but there is an error when Agent tries to publish a comment. | Admin Panel |  | done
22 | Static boxes have an orange background. We want transparent as the content should be the only thing shown - no orange background. | Homepage, pg. #6, 7 | What is the size and dimensions of the static boxes? | D(leave)
23 | Close a Ticket | Admin Panel | Show more clearly the option to close a ticket.
24 | Trail of Agents that were assigned a ticket and who closed a ticket not visible. | Admin Panel | Important so can monitor agents.
25 | Monitor Agents on side-menu bar shows no results even though agents have been assigned tickets during testing. | Admin Panel | The information does not show who actioned the ticket, who closed the ticket etc.
26 | How can conversions be seen on the Admin Panel? | Conversion | Agent/Admin do not know if there has been a conversion.
27 | If the customer decides to change their review and convert - the conversion does not lead to a notification on the review. | Conversion | That review for records on the front end and backend should show that this ticket rating has been converted from negative to positive.
28 | Registered companies from the Admin Panel do not reflect on the 'Registered Companies' tab | Reviews
29 | How to show if a ticket is closed? | Admin Panel | Any notification etc.?
30 | How to batch comments to assign and publish after approval | Admin Panel | Pending | notification table for sr. Agents and jr. Agent
31 | How to differentiate the Suppliers Response on the comments expanded view from other comments? | Reviews | So on first sight, user knows that this is a supplier response | after design
32 | If reset password - why does customer need to confirm their account again? |  | Notification on screen that account needs to be confirmed after password reset. But the email never comes on the address for the user to confirm their account. | D
33 | Review message history does not show the supplier has responded | Admin Panel | Can discuss on Skype to explain properly. | add column
34 | Notes section on reviews as discussed to write comments on that ticket visible to all agents that action that review. | Admin Panel |  | D
35 | Date of Review on admin panel for tickets is incorrect | Admin Panel | Review was left on 23 Feb, admin panel shows the same ticket no. review was left on 21 Feb.
36 | Archived files - does not show which ticket no. the file was archived for. | Admin Panel | Under dashboard section archive files() | archive link(access rights senior agent and admin)
37 | Notification to show that Agent has actioned that ticket and it is not waiting for approval for the SR Agent/Admin | Admin Panel | How to batch reviews for the SR Agent/Admin if you are JR Agent.
38 | How the SR Agent/Admin know which review is waiting for approval to be published. | Admin Panel | There is no notification that the SR Agent knows which review needs to be approved from the JR Agent so it can be published.
39 | Homepage - Click on company hyperlink | Review | This opens all the reviews for that company but the date should be displaying from most recent first/on top. | D
40 | Reporting | Admin Panel | Can I please discuss this on Skype, as there are many reports that do not work (error notification), and I am unable to extract several that were agreed on.